# Project Completion Plan: Project Nexus

Project Title: Nexus: Agentic Client Knowledge System (Account Intelligence Layer)

## 1. Executive Summary

Team Trojan Horse has successfully transitioned Project Nexus from a conceptual charter to a high-fidelity intelligence platform. The system consolidates unstructured account data from Google Workspace and Basecamp into a unified "One Source of Truth" architecture. Despite a condensed 12-day sprint and incremental technical hurdles in RAG logic and RBAC implementation, the group delivered a functional multi-agent MVP that meets all strategic benchmarks for retrieval accuracy and system stability

### 1.1 Team Personnel & Functional Units

The project was executed through four specialized functional units, lead by the following team members:

| Functional Unit | Lead | Primary Technical Contribution |
| --- | --- | --- |
| Data Engineering | Aryan | Ingestion Pipeline Construction; Vector Embeddings optimization; ChromaDB/Pinecone storage architecture. |
| AI Architecture | Khush | Multi-Agent Classifier Engineering; LangGraph orchestration of 5 specialized agents; RAG grounding engine. |
| Systems & API | Parshwa | FastAPI Ecosystem (38+ Endpoints); "7 Living Documents" requirement analysis; Global Role Matrix & RBAC. |
| Frontend Design | Saanvi | ReactJS + Tailwind CSS Implementation; System-to-UI translation; Responsive dashboard development. |

## 2. Project Objective & Success Measurement

### 2.1 Final Goal Achievement

The group successfully deployed an Agentic AI system that centralizes intelligence from Google Mail, Chat, and Drive. The multi-agent model (Historian, PM, Tech Lead, Auditor, Strategist) provides a structured, searchable knowledge graph accessible via the Nexus Dashboard.

### 2.2 Success Metrics (Group Totals)

- Ingestion Coverage: Targeted Google Workspace and Basecamp streams successfully mapped.

- System Latency: Average query response time maintained through API and database indexing optimizations.

- Retrieval Accuracy: Achieved good accuracy rate in agentic response grounding.

- Security Compliance: 70% implementation of the granular Role-Based Access Control (RBAC) matrix.

## 3. Detailed Deliverables & Assets

The following collective assets are finalized and stored in the GitHub organization repository:

- Project Codebase: Full-stack repository containing the FastAPI backend and React + TypeScript frontend.

- Agentic Engine: Comprehensive LangGraph workflow featuring 5 specialized agents.

- Data Infrastructure: Configured Vector Store (ChromaDB/Pinecone) and Python-based data cleaning pipelines.

- Documentation Suite: Project_Charter.pdf, Project_Completion_Plan.md, and Architecture Diagrams.

- API Management: Validated Postman collection covering Auth, Discovery, and Ingestion endpoints.

## 4. Final Work Breakdown Structure (Group Actuals)

| WBS ID | Task/Milestone Name | Task Type | Dependency | Unit Responsible | Start Date | End Date | Deliverable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | MILESTONE: Planning Complete | Sequential | - | Systems Unit | 2026-01-19 | 2026-01-19 | Signed Charter |
| 1.1 | Technical Architecture Design | Sequential | - | Data & Systems | 2026-01-19 | 2026-01-19 | Architecture Doc |
| 1.2 | Multi-Agent Flow Mapping | Parallel | 1.1 | AI Unit | 2026-01-19 | 2026-01-20 | LangGraph Diagram |
| 2.0 | MILESTONE: AI Core Ready | Sequential | 1.2 | AI Unit | 2026-01-20 | 2026-01-24 | Intelligence Layer |
| 2.1 | Ingestion Pipeline Development | Sequential | 1.2 | Data Unit | 2026-01-20 | 2026-01-22 | Ingestor Code |
| 2.2 | Agent Classifier Construction | Sequential | 1.2 | AI Unit | 2026-01-21 | 2026-01-23 | Agentic Engine |
| 2.3 | Vector DB Indexing | Sequential | 2.1 | Data Unit | 2026-01-23 | 2026-01-24 | Pinecone Index |
| 3.0 | MILESTONE: Platform Integration | Sequential | 2.3 | Systems Unit | 2026-01-25 | 2026-02-02 | Functional App |
| 3.1 | FastAPI Endpoint Deployment | Parallel | 2.2 | Systems Unit | 2026-01-25 | 2026-01-27 | API Swagger |
| 3.2 | RAG Grounding Refinement | Sequential | 2.2 | AI Unit | 2026-01-25 | 2026-01-27 | RAG Logic (2-Day Lag) |
| 3.3 | Dashboard Implementation | Sequential | 3.1, 3.2 | Frontend Unit | 2026-01-28 | 2026-02-02 | UI Sync (3-Day Lag) |
| 4.0 | MILESTONE: Project Closure | Sequential | 3.3 | All Units | 2026-02-03 | 2026-02-05 | Final Handover |
| 4.1 | Stress Testing & Benchmarking | Sequential | 3.3 | Data & AI Units | 2026-02-03 | 2026-02-04 | Performance Report |
| 4.2 | Master GitHub Submission | Sequential | 4.1 | Group 3 | 2026-02-05 | 2026-02-05 | Final Codebase |

## 5. Challenges & Mitigation Strategies

- Unstructured Data Noise: Initial raw data caused classification errors. Mitigation: The Data Unit (Aryan) implemented a custom pre-processing reducer to clean 40% of input volume.

- Multi-Agent Conflict: Agents occasionally provided overlapping updates. Mitigation: The AI Unit (Khush) engineered a "State Reducer" within LangGraph to synthesize conflicting outputs.

- Integration Latency: RBAC checks created a performance bottleneck. Mitigation: The Systems Unit (Parshwa) optimized database query logic and implemented caching for permission flags.

## 6. Future Plans & Sustainability

- Continuous Improvement: The AI Unit will monitor and tune agent prompts to minimize hallucination risks.

- Maintenance: The Data Unit has scheduled automated monthly re-indexing of the vector store.

- Roadmap: The Group plans to finalize the remaining 20% of the RBAC functionality and explore Jira integration.

## 7. Post-Presentation Feedback & Roadmap

Following the final project presentation, the team received critical inputs from Account Management (AM) stakeholders. These insights have been used to define the next phase of development, split between internal optimization and external feature delivery.

### 7.1 Key Feedback Points

- Account Manager Input: Stakeholders requested more granular visibility into "Upsell Opportunities"—currently, the system identifies context but lacks a proactive sales recommendation engine.

- Data Quality Concerns: AMs noted that "Tribal Knowledge" in chats is often messy; the system needs a better filter for informal vs. professional insights.

- Scalability: The ability to ingest specific streams based on "What they use" (Client-specific toolstacks) rather than a global "Ingest All" approach.

### 7.2 Milestone-Based Strategy (Google Sheet Reference)

Note: The detailed actual vs. planned dates are maintained in the project's tracking Google Sheet.

| Milestone | Type | Planned (Sheet Date) | Current Status | Key Focus |
| --- | --- | --- | --- | --- |
| Q1 Refinement | Internal | 2026-03-15 | Scheduled | Data quality cleaning & noise reduction in Chat. |
| Upsell Engine | External | 2026-04-10 | Planning | Mapping extracted context to AM service offerings. |
| Dynamic Ingest | Internal | 2026-05-01 | Research | Toggle-based ingestion for custom client toolstacks. |

### 7.3 Strategic Roadmaps

#### A. Internal Roadmap (Technical & Operations)

- Ingestion Logic Upgrade: Shift from "Bulk Ingest" to "Selective Stream Ingest" based on account usage profiles.

- Data Quality Layer: Implement a secondary LLM "Validator" to score data reliability before it hits the Project Graph.

- Reducer Efficiency: Further optimize the LangGraph reducer to handle high-frequency chat updates without state drift.

#### B. External Roadmap (Stakeholder & Commercial)

- Opportunity Discovery: Add an "Upsell & Expansion" tab to the dashboard using an Agentic Strategist to highlight revenue gaps.

- Client Toolstack Personalization: Allow Account Managers to select which data sources (e.g., just Drive and Mail, skip Basecamp) are used for a specific project.

- Executive Summary View: A high-level view for senior leadership summarizing account health without the technical logs.

Final Approval: Next-phase roadmap is approved for execution starting as soon as possible.